## Sheet1
1 | Risk No. | Risk Category | Risk Title | Risk | Consequence | Risk Level at start* | Date Identified | Last reviewed | Risk Owner | Risk Strategy | Mitigations | Risk level at latest review | Delivery of risk mitigating actions - update | Next Review Date
| 1 | Finance | Reduced income | LA and CCG core funding is reduced | Inability to meet contractual obligations | 3x5=15 | 2018-08-01 | 2020-04-27 | Board | Accept and Mitigate | Demonstration of impact and effectiveness. Broadening of income streams. Maintain reserves at recommended level. | 3x3=9 | Review April 20. Budget for 19/20 is satisfactory. Sound relationships with commissioners. | 2020-07-01
| 2 | Organisational | Partnerships | Lack of support from key partner organisations | Reduced impact and limited opportunities to reach communities and make their views count | 3 x4 = 12 | 2018-08-01 | 2020-04-01 | Board | Accept and Mitigate | Relationship building. Demonstrating and communicating benefits to all and willingness to share. MoUs. Improved peformance. | 3x3=9 | After one year CPFT have not managed to sign off our MoU with them. As a result joint projects are still problematic at times. Review CPFT have now signed the MoU. Risk reduced to RAG rating Amber. 9. Oct 19. Review Position unchanged April 20. | 2020-07-01
| 3 | Reputational | Low and uncertain profile | Covid -19 crisis including lockdown leads to loss of effectiveness in core business | Reputation is damaged and partners question our viability | 3x4=12 | 2020-04-27 |  | Board | Accept and Mitigate | Ensure good conditions for home working. Ensure team cohesion through weekly meetings. Further strengthen on line comms and presence |  |  | 2020-07-01
| 4 | Organisational | Loss of contract | Covid-19 crisis creates highly volatile situation in next 6 months with emergency decisions being made | Major instability for SUN Network. | 2x5=10 | 2020-04-01 |  | Board | Accept and Mitigate | Maintain solid performance and good rels with commissioners. Monitor local situation closely. |  |  | 2020-07-01

## Matrices
Significant effect
Probably will happen
4
Noticeable effect
Quite possibly will happen
3
Small effect
Very unlikely to happen
2
Negligible
Almost certainly will not happen
1
Impact
Probability
4
3
2
1
L
L
L
L
1
M
L
L
L
2
H
M
L
L
3
H
H
M
L
4